Chapter VIII

Closeout

| VIII. Closeout | 8-2 |
| --- | --- |
| A. Overview | 8-2 |
| B. Deadlines, Penalties and Extensions | 8-3 |
| i. Penalties | 8-3 |
| ii. Extensions | 8-3 |
| C. Federal Grant Tracking System Closeout Process | 8-4 |
| Table 18. HSO Closeout Process | 8-4 |
| D. Grant File Closeout | 8-5 |
| E. Financial Obligation Closeout | 8-6 |

# VIII. Closeout

This chapter outlines the required process for closing out the Federal fiscal year including Department and National Highway Traffic Safety Administration (NHTSA) requirements.

# A. Overview

This section provides an overview of the Federal fiscal year closeout process.

Grant and the Federal fiscal year closeout activities begin when all required progress reports, Final Reports and final invoices have been received from subrecipients by the Highway Safety Office (HSO).

When final claims are processed, the Department procedures for submittal of the final Federal reimbursement voucher must be followed. Included in this process is the final determination of the amount of program funds actually expended and the under-run amount which is available for carry forward to the new program year.

Part of this process also involves the final determination of the amount of Federal funds expended for local share (40 percent minimum required), see 23 CFR Part 1300.13(b), and that the State and local match to the program met or exceeded the minimums based on the Federal funding source requirements. See Chapter VI. Fiscal Procedures, Section C, Matching Funds.

Beginning with FY 2023, NHTSA’s Final Rule provides that States must submit the final voucher within 120 days after the end of the fiscal year (January 28), see 23 CFR Part 1300.33(d). This is consistent with the extension for closeout provided in the Uniform Guidance at 2 CFR Part 200.344 Closeout.

# B. Deadlines, Penalties and Extensions

This section describes the required deadlines for annually closing out the HSO grant file.

The State’s AGA for a fiscal year and the State’s authority to incur costs under that plan expire on the last day of the fiscal year. The State is not permitted to extend the right to incur costs under the old fiscal year’s AGA. Grant funds remaining at the end of the fiscal year and the expiration of a AGA are immediately available for expenditure during the next fiscal year provided the State has a new AGA approved by NHTSA including any amendments, see 23 CFR Part 1300.41. See also Chapter II. Planning, Section Q. Three Years Plus One Federal Obligation Restriction.

The Uniform Guidance provides that the pass-through entity (HSO) will closeout the Federal award when it determines that all applicable administrative actions and all required work of the Federal award have been completed by the non-Federal entity. See 2 CFR Part 200.344 Closeout for the actions the non-Federal entity and Federal awarding agency or pass-through entity must take to complete this process at the end of the period of performance.

In addition to actual costs to be reimbursed to the State, the State’s share of matching funds must be finally calculated based on the final expenditures and entered into the GTS. This calculation determines the total funds, Federal and State matching, which have been spent for NHTSA funding sources.

The HSO is required to submit the State’s final billing for the closing grant year to NHTSA by January 28. In order to meet the annual closeout deadline, all final Project Reimbursement Claims must be received by the HSO from subrecipients by (December 15 or other date established by the State) and be entered for payment into the State Accounting System by [insert appropriate date]. Any invoices received from subrecipients after (December 15 or other date established by the State) cannot be processed or approved for payment with Federal funding.

The expiration of the AGA does not affect the ability of NHTSA to disallow costs and recover funds on the basis of a later audit or other review or the State’s obligation to return any funds due as a result of later refunds, corrections or other transactions, see 23 CFR Part 1300.42.

i. Penalties

The final voucher submitted by the State must meet the requirements of 23 CFR Part 1300.33(b) and be submitted within 120 days after the THSP expiration. The final voucher constitutes the final financial reconciliation for each fiscal year, see 23 CFR Part 1300.40. Failure to provide the information specified shall result in rejection of the voucher.

ii. Extensions

Extraordinary circumstances consistent with 2 CFR Part 200.344 Closeout and 2 CFR Part 200.345 to request an extension for submitting a final voucher may be brought to the attention of the NHTSA Regional Administrator by the HSO Administrator. The extension may not exceed 30 days. The State submits a written request for an extension which describes the extraordinary circumstances necessitating an extension. The approval of any such extension request is required to be in writing, to specify the new deadline for submitting the final voucher and shall be signed by the NHTSA Regional Administrator (Approving Official).

All grant related records shall be retained for at least three years from the date the final voucher is submitted to NHTSA.

# C.  Federal Grant Tracking System Closeout Process

This section describes the final reimbursement voucher process completed by the HSO and other Department sections to closeout using the Federal Grant Tracking System (GTS).

The HSO Vouchering Process for project closeout and final reimbursement is as follows:

[NOTE: The following table is based upon the closeout process used by the Alaska Highway Safety Office and may vary in the State. Insert the appropriate titles of HSO Staff from your State in the Process detailed below.]

Table 18. HSO Closeout Process

| Responsible Person | Action |
| --- | --- |
| Final invoice received by: [name} | Date stamps invoice and routes to [name] |
|  | Reviews and ensures compliance with grant agreement and receipt of subrecipient’s Final Report As necessary, obtain additional supporting documentation from subrecipient or return to agency for completion Signs with notation, “ok to pay” Forwards to [name |
|  | Determines all final invoices have been received for the grant year (Deadline December 15) Submits invoices to Finance office for final payments by January 1 Sends email notification to [name] section that final invoices have been paid Determines the final required matching shares and 40 percent share to locals’ amount and transmits information to [name] Notifies the HSO administrator of the amount of known carry forward funding by funding source, if any, for programming in the next fiscal year |
|  | Conducts standard invoice payment reconciliation processes Enters final invoice postings to the GTS Works with the HSO to check accuracy of information and enters required State matching share and 40 percent share to locals to GTS Closes out the HSO fiscal year |

See also Section B. Deadline, Penalties and Extensions, and Chapter VI. Fiscal Procedures, Section A. In-house Grant Payment and Federal Reimbursement Voucher Process.

# D. Grant File Closeout

This section provides the process for physically closing grant files at the end of the fiscal year.

After the final Federal reimbursement voucher for the grant year has been submitted, the HSO closes out each grant number and file for that fiscal year. The [insert position title] is responsible for completing the grant file closeout. Each file will be reviewed for completeness, accuracy of filing and resolution of any pending matters.

# E. Financial Obligation Closeout

This section provides the NHTSA requirements for preparing the financial obligation closeout at the end of the fiscal year.

The financial obligation closeout is a final accounting of all HSO expenditures for the year. As required in       23 CFR Part 1300.40 the financial closeout will include the final official voucher for total expenses incurred which satisfies the Federal requirements in 23 CFR Part 1300.33(b).

The required information for the voucher was changed in the NHTSA Final Rule beginning FY 2024 at 23 CFR Part 1300.33(b). See Chapter VI. Fiscal Procedures, Section A. subsection iv. Submission of Federal Reimbursement Voucher, for the Federal requirements for voucher content.

New and changed codes for eligible uses under the BIL beginning FY 2024 will be available on GTS June 1, 2023. There will also be supplemental funds released, States can use either regular or supplemental funds. When submitting vouchers, the State may need to upload an explanatory form if there are projects which have more than one eligible use.

See Chapter II. Planning. Section Q. Three Years Plus One Federal Obligation Restriction