### Chapter IV

Grant Selection and Execution

| IV. Grant Selection and Execution IV. Grant Selection and Execution | 4-2 |
| --- | --- |
| A. Proposed Grant Application Submission Process | 4-2 |
| B. Grant Application/Distribution Log | 4-4 |
| C. Grant Selection Process | 4-5 |
| i. HSO Initial Review | 4-5 |
| ii. Grant Review Team | 4-6 |
| iii. Grant Proposal Evaluation Procedure | 4-6 |
| iv. Risk Assessment | 4-7 |
| v. Grant Negotiations | 4-7 |
| Table 8. Project Proposal and Grant Agreement Preparation Process Overview | 4-8 |
| vi. Award | 4-8 |
| vii. Debriefing Conferences | 4-8 |
| D. Final Grant Agreement Preparation | 4-9 |
| i. Federal Requirements (Uniform Guidance) | 4-9 |
| ii. Special Conditions | 4-9 |
| iii. Signatures | 4-9 |
| iv. Subrecipient Certification | 4-10 |
| E. NHTSA Equipment Purchase and Disposition Approval of $5,000 or More | 4-12 |
| F. Reporting Requirements | 4-14 |
| i. Quarterly Progress Reports | 4-14 |
| ii. Final Progress Report | 4-14 |
| iii. Special Progress Reporting | 4-14 |
| G. Grant and THSP Revisions | 4-15 |
| H. Development of Highway Safety Office Internal Grants | 4-17 |
| i. P&A Match Requirement | 4-17 |
| ii. HSO Employee Time Allocation and Certification Requirements | 4-18 |
| iii. Time and Attendance Records | 4-19 |
| iv. Subrecipient Timekeeping Requirements | 4-19 |
| v. HSO Invoicing and Reporting | 4-19 |

Chapter IV contains information on the Highway Safety Office (HSO) process for selecting proposed grant applications for funding. Amendments to signed grant agreements and other special requirements are also explained.

### A. Proposed Grant Application Submission Process

This section describes the HSO proposed grant application (project agreement) submission process.

[NOTE: The grant selection process described in this, and subsequent chapters is the one used by the Alaska Highway Safety Office. Alaska utilizes a Grant Review Team as part of this process. The information in this and related chapters may need to be modified to align with the HSO process actually used by the State.]

Traffic safety grant selection procedures that fully comply with the State and Federal regulations shall be published and used by the HSO. Only grant applications that address the traffic safety issues identified through the Triennial Highway Safety Plan (THSP) problem identification process, or later amendments to the THSP in the Annual Grant Application (AGA), shall be accepted. The grant selection procedure shall be reviewed and updated annually. A Request for Proposal (RFP) package shall be posted by the HSO on the web site to ensure adequate and uniform notice to all prospective subrecipients of the prescribed requirements and deadlines.

The following agencies/organizations are eligible to submit applications for HSO traffic safety grants:

- State agencies

- Cities, counties and their sub agencies

- Non-profit organizations with existing IRS 501(c)(3) status

[NOTE: Your State may not allow non-profit organizations to obtain grants.]

Proposals must comply with the conditions described in Chapter II. Planning, Section F(iii) Countermeasure Strategies for Funding.

Applicants are directed to the HSO RFP for the current grant year which is available on the web site for a complete set of submission instructions and for the application form. The HSO RFP contains the deadlines for submission. In lieu of a pre-proposal conference, applicants are asked to address questions to the HSO [insert position title] by mail, telephone, fax or email.

Proposal Submission Instructions:

- Only one copy of the proposed grant application should be submitted, and it is preferred that the application be submitted by email. A hard copy of the application with original signatures must also be mailed to the HSO or faxed (if faxed, a hard copy of the application with original signatures must be mailed to the HSO). (Some States now have electronic grant systems. In that case, the specific procedures and requirements for accessing the electronic system should be included here.)

- Late applications will not be accepted.

- Mailed or faxed applications received by the HSO will be directed to the [insert position title].

- Applicants mailing applications will be instructed to allow normal mail delivery time to insure timely receipt. Applicants assume the risk of non-delivery or late arrival associated with the method of delivery selected. The HSO assumes no responsibility for delays caused by external delivery systems.

- The HSO will notify applicants by email of receipt of their applications within five days of receipt.

- Applicants who do not receive a notice within ten days of submitting their application must contact the HSO to confirm that their application has arrived at the HSO if their application is to be considered for selection.

- Organizations claiming non-profit or not-for-profit status must submit, with their application, a letter showing current 501(c) (3) status has been granted by the IRS.

[NOTE: The HSO policy described in the following paragraph may vary in other States.]

If a single subrecipient is requesting a grant under multiple Federal program funding sections/sources, then the subrecipient must submit separate applications to the HSO for each program and identify specific dollar amounts for each funding section/source.

### B. Grant Application/Distribution Log

This section describes the process for the HSO to track the receipt of proposed grant applications.

The HSO Grant Distribution Log form (a HSO Excel spreadsheet) should be created to track the receipt and handling of all proposed grant applications received by the HSO annually. The purpose of the log is to assure that all required actions are completed and in a timely manner. The contents of the log should be listed here: [insert each item specified in the log]

The HSO [insert position title] is responsible for making the initial entries and periodically updating the HSO Grant Distribution Log to reflect the status of the applications.

(Some States now have electronic grant application and tracking systems. In that case, the specific procedure and requirements for using the electronic system should be included here.)

### C. Grant Selection Process

This section describes the HSO grant selection process.

i. HSO Initial Review

Proposed grant applications are first reviewed internally by the HSO [insert position titles] and then by the [insert title] to:

- Ensure that the application meets the required criteria.

- Check for budget availability and available resources.

- Compare the application with current activities.

- Determine whether the proposed grant activity will impact traffic safety, will work toward established targets by ensuring that the problem is adequately described, and that objectives, performance measures, and resources requested will address the problem.

- Determine that the potential subrecipient is the appropriate entity to perform the activities.

See Chapter III. Project Development, Section D. Grant Development Calendar for applicable timelines.

A Grant Review Form will be completed by HSO reviewing staff to record all comments, questions and additional information obtained from the applicant. After the first review of each proposed grant application within the HSO, the [insert position title] will request any additional information needed by contacting the applicant or others as necessary and recording their responses on the Grant Review Form. When completed the [insert position title] will print the Grant Review Form and circulate it to the [insert position title] and the [insert position title] for review and confirmation that all pending issues have been addressed. The proposal will then be forwarded, using the prescribed HSO process, to the Grant Review Team for consideration. (Some States now have electronic grant systems which include the review and approval process. In that case, the specific procedures, and requirements for using the electronic system should be included here.)

The determination of whether the application has the potential to impact traffic safety goals will be based on its ability to implement evidence-based strategies, show a commitment to sustain and contribute to success, have measurable, specific outcomes and address the greatest demonstrable need/problem. Proposals that target underserved and overrepresented communities, high-risk populations, high-risk behaviors and high crash locations will receive additional consideration. Proposals must comply with the conditions described in Chapter II. Planning, Section F(iii) Countermeasure Strategies for Funding.

Following are some guiding questions for HSO staff conducting a technical analysis of a proposed grant application:

- Has a traffic-safety related problem been adequately identified and appropriately described in the problem statement?

- Do the objectives, targets and performance measures directly address the identified problem?

- Are the objectives specific, clearly stated and achievable?

  - Is a completion date indicated for each objective?

  - Is sufficient time allocated to achieve each objective?

- Will performance measures provide adequate evidence of project activity and accomplishment of objectives?

- Are personnel needs accurately identified? For example:

  - If an objective requires roadway safety studies, an engineer must be involved.

  - If an objective involves public information and education activity, does the subrecipient have the resources available to perform and complete the activity?  Is the subrecipient aware of the HSO’s traffic safety public information and education policies and are they able to meet the requirements?

  - If the objectives involve law enforcement agencies, a sufficient number of appropriately trained officers must be available.

- Will any special equipment be needed?  If so, will it be available for grant implementation, or does the applicant require funding to acquire the equipment?

- Are there other considerations that might affect subrecipient performance?  If so, are they adequately addressed?

## ii. Grant Review Team

[NOTE: Every State should have a process for evaluation of proposed grant applications. The following example utilizes a Grant Review Team. The State may use a different approach.]

Proposals recommended for funding after the initial review by the HSO staff are then evaluated by the Grant Review Team (GRT). The GRT is composed of representatives of agencies and organizations selected by the HSO Administrator who have worked with the HSO in the past and have traffic safety or grant-related experience. The GRT was created to review and score proposals to establish a fair process for selecting grants. Applications are prescreened by the HSO before being sent to the GRT members. Only qualified grant applicants are forwarded to the GRT. If the GRT recommends changes to any application, those changes will be negotiated by the HSO [insert position title].

To avoid any conflict of interest, the GRT members are requested to sign a statement provided by the HSO (See Appendix B. Non-Conflict of Interest Statement).

## iii. Grant Proposal Evaluation Procedure:

- When the grant reviewer has received an application, they read through each one completely, at least one time with no points awarded. This method ensures a full understanding of each proposal before awarding points. It also will help to eliminate or reduce the psychological tendency to award fewer points to the first offer reviewed.

- Each grant reviewer will be supplied with a scoring sheet developed by the HSO for the application being reviewed (See Appendix C. Grant Scoring Criteria). While scoring, only whole numbers (not 3.5 or 4.76) will be used. Numbers may be selected between the scoring criteria, i.e., 1, 2, or 4, if a proposal falls between the criteria descriptions.

- Comments should be added as needed for clarification on the reason points were given. The application reviewer may "insert comment" directly into the field, add to the bottom of the scoring sheet, or supply comments on a separate document. Grant reviewers are not responsible for determining the actual award of the proposal; they are only scoring the proposal. Offers will be determined upon a compilation of points awarded as a combined effort of the GRT scoring and the HSO.

- Once a reviewer is satisfied with their review, they will perform a “File, save as”, rename their electronic scoring sheet according to the application reviewed and submit the results via email to the HSO [insert position title] on or before the deadline. Reviews can also be faxed.

- Any questions identified by the GRT members will be resolved by the HSO [insert position title] before a final selection is made by the HSO.

- Final selections are made only with the approval of the HSO Administrator. There must be a separation of duties between the individual responsible for developing the grant and the individual who approved the grant.

## iv. Risk Assessment

The HSO shall develop and follow a procedure to conduct a risk evaluation for each subrecipient (not contractors) receiving NHTSA funds. The HSO, as a pass-through entity, is required to evaluate each subrecipient’s risk of noncompliance with Federal statutes, regulations and the terms and conditions of the sub award for purposes of determining the appropriate subrecipient monitoring. Pass-through entities may use judgment regarding the most appropriate timing for the assessments however it is a best practice to evaluate risk prior to making a subaward. The HSO shall develop, implement and document the outcome of a risk assessment process and may consider the four factors listed in 2 CFR Part 200.332(b).

(1) The subrecipient's prior experience with the same or similar sub awards.

(2) The results of previous audits including whether or not the subrecipient receives a Single 	Audit in accordance with 2 CFR Subpart F

(3) Whether the subrecipient has new personnel or new or substantially changed systems; and

(4) The extent and results of Federal awarding agency monitoring (e.g., if the subrecipient also 	receives Federal awards directly from a Federal awarding agency).

If a subrecipient of the HSO passes on Federal grant funds via a sub award, the subrecipient has the same obligation as a pass-through entity for all requirements of 2 CFR Part 200.332 including conducting a risk assessment of their sub recipient.

The HSO shall consider imposing specific sub award conditions upon a subrecipient if appropriate as described in 2 CFR Part 200.208 Specific conditions. See also Chapter V, Section N. Monitoring.

## v. Grant Negotiations

After a successful applicant has been notified that their proposed grant application has been accepted, the applicant completes any final grant agreement development issues through negotiations and discussions with the HSO [insert position title]. The grant agreement outlines the specific components of a project, the final authorized budget, the specific performance measures and objectives, and the commitment of responsibilities by the HSO and the subrecipient.

Final grant agreement development typically involves some level of negotiation to ensure that the final agreement meets all of the HSO requirements, expectations and conditions. The [insert position title] negotiates on behalf of the HSO. Negotiation allows the HSO and the applicant to arrive at an understanding on the specific details of the grant agreement (such as budget detail amounts, enforcement activity locations, evaluation criteria, etc.). Negotiating involves discussion, clarification, or modifications to the proposed grant application. Items to be discussed during the negotiation phase include, but are not limited to, the following:

- Problem identification

- Project description

- Anticipated outcome

- Time period

- Location and frequency of activity

- Acquisition of equipment or other items

- Frequency of reporting and invoice submissions

- Budget content

- Performance measures

The following table lists the steps a typical proposed grant application follows from initial development to final grant agreement execution. Also shown are the parties responsible for each step.

Table 8. Project Proposal and Grant Agreement Preparation Process Overview

| Step | Action | Responsible Parties |
| --- | --- | --- |
| 1. | Project development and proposed grant application submission | Applicant |
| 2. | Receive proposed grant application, print and log in | [insert position title] (Grant Distribution Log) |
| 3. | Proposed grant application review and clarification with Applicant | [insert position title], Applicant |
| 4. | Technical analysis and HSO pre-selection | [insert position title(s)], HSO Administrator (Grant Review Form) |
| 5. | Scoring | GRT |
| 6a. | Final Grant Agreement Negotiation | [insert position title], Subrecipient |
| 6b. | Pre-award Risk Assessment | [insert position title] |
| 7. | HSO Formal Approval | HSO Administrator |
| 8. | Department Approval | [insert position title] |
| 9. | Inclusion in the AGA for NHTSA Region approval | [insert position title) |
| 10. | After NHTSA approval received, Notice to Proceed (NTP) | [insert position title] |

## vi. Award

[NOTE: The HSO procedure in the following paragraph may vary.]

Where possible, all applicants will be notified in writing of their award status by September 1. Following successful completion of negotiations and receipt of all required documentation, the HSO issues a NTP to each successful applicant by October 1 of the new grant year. Each NTP shall be signed by the HSO Administrator and the [insert position title].

## vii. Debriefing Conferences

Upon request, a debriefing conference may be scheduled for an unsuccessful applicant by contacting the [insert position title] no later than [“X”] business days after receiving notice that the proposed grant application was not accepted. The HSO will schedule the debriefing conference within [“X”] to [“X”] business days of the request. The HSO may conduct debriefing conferences in person or by telephone. Discussion will be limited to a critique of the proposed grant application. Comparisons between other applications or evaluations of other applications are not permitted.

### D. Final Grant Agreement Preparation

This section provides guidance for the preparation of proposed grant applications into a final grant agreement.

## i. Federal Requirements (Uniform Guidance)

Every subaward must be clearly identified to the subrecipient as a subaward and include the following information (including action if any changes are made in subsequent subaward modifications) as required by 2 CFR Part 200.332 : Federal Award Identification, subrecipient name, subrecipient’s unique entity identifier; Federal Award Identification Number (FAIN)*; Federal award date; subaward performance start and end date; amount of Federal funds obligated by the action; total amount of Federal funds obligated to the subrecipient; total amount of Federal award; award project description (FATA), name of Federal awarding agency, pass-through entity and contact information for awarding official; assistance listing number and title; whether the award is Research and Development; indirect cost rate (if any) including if de minimis rate is charged; requirements imposed by Federal statutes, regulations and terms and conditions of the award; any additional requirements; an approved federally recognized indirect cost rate (if any) negotiated with the Federal government or the pass-through entity or the 10 percent di minimis rate; requirement for access by auditors to records and financial statements and appropriate terms and conditions concerning closeout of the award.

*On November 23, 2022, NHTSA issued written Guidance to assist States in identifying the FAIN in advance to be used for a specific subaward. The guidance is intended to assist HSOs comply with the government-wide requirements related to FAIN for subawards for both the Uniform Guidance and the federal Transparency Act. The NHTSA Regional Office should be contacted with any questions and/or issues.  When more than one funding source is used and needs to be split across multiple FAINs, the HSO should select the minimum number of FAINs that represent the year(s) of funding most likely to be used. In addition, the HSO is responsible for properly documenting within their financial systems the actual FAIN for all federal awards received and expended.

## ii. Special Conditions

In addition to the general required terms and conditions which apply to every traffic safety grant agreement, the HSO may determine that special conditions should be imposed upon a specific subrecipient. Some reasons for the special condition may be the results of the pre-award risk assessment, nature of the specific strategy being addressed, past experience with the subrecipient or a special requirement that is not otherwise addressed in the general terms and conditions. If a special condition is imposed upon a subrecipient, the special condition shall be documented in the HSO NTP. Following are some examples of a special condition:

- The subrecipient is allowed to charge costs to the grant for activity which takes place within a stated timeframe before the official start date of the grant (this is typically a rare occasion which may occur when preparatory activity is necessary in order to assure that the primary grant activity can begin on the start date of the new fiscal year)

- The subrecipient is required to share equipment purchased under the grant with other agencies in their geographic region.

- The subrecipient is limited to using specific personnel to complete grant activity.

## iii. Signatures

## a. HSO requirements

When the HSO Administrator executes a grant agreement by signing it, he or she is certifying that the agreement:

- Is legal and payable.

- Includes all required and applicable provisions.

- Complies with all applicable Federal and State regulations and laws.

- Has received Federal approval when needed.

- Has been budgeted with available funds.

- Has been authorized by the HSO as part of the THSP or as an amendment to the THSP made in the AGA.

Before approval, the [insert position title] will review all grant agreements for form and content, applicable provisions, eligibility of costs, consistency, and accuracy.

## b. Subrecipient requirements

A final grant agreement submitted to the HSO must be signed by the authorizing official (person with contracting authority) for the applicant agency or organization. The authorizing official, and in some cases the Project Director, must also certify and ensure that all of the conditions contained in the Subrecipient Certifications and Assurances, Reporting Requirements and Invoicing Requirements will be met including any special conditions.

For local grants, the agreement must be made with the unit of local government or political subdivision of the State, not with an operating division or function of the local governmental unit or political subdivision of the State. Likewise, for statewide grants, the agreement must be made with the parent agency, not a bureau or division.

A grant agreement must be approved and executed in accordance with subrecipient procedures as well. This may involve placement on the agenda for a city council meeting, the county commissioners’ court, or a State agency’s director, board, or commission. Scheduling time frames vary from agency to agency. Some local governments require agenda items to be heard at three consecutive meetings which adds significantly to the time required for grant agreement approval. Scheduling requirements must be considered in the approval process to ensure that the grant can be activated on time.

## c. Educational institutions and hospitals

2 CFR Part 200 Appendix III requires that educational institutions and hospitals provide a “Certificate of Indirect Costs (F&A) Costs” for federally funded projects. The certificate must be signed on behalf of the institution by the chief financial officer, or an individual designated by an individual at a level no lower than vice president or chief financial officer. An indirect (F&A) cost rate is not binding upon the Federal Government if the most recent required proposal from the institution has not been certified. 2 CFR Part 200 Appendix IX  states that the existing OMB principles located at 45 CFR Part 75 Appendix E, entitled “Principles for Determining Cost Applicable to Research and Development Under Grants and Contracts with Hospitals,” remain in effect until such time as revised OMB guidance is proposed and implemented for hospitals.

iv. Subrecipient Certification

The HSO Grant Request/Project Agreement form, and contracts must contain required terms and conditions as well as requiring compliance with the Federal Certifications and Assurances which pertain to subrecipients. These sections provide the terms and conditions governing the grant or contract and certifies that a subrecipient will comply with the applicable regulations, policies, guidelines, and requirements as they relate to the application, acceptance, and use of Federal or State funds for the project.

The subrecipient or contractor must be aware of the requirements imposed upon them, see 23 CFR Part 1300 Appendix A Certifications and Assurances and  2 CFR Part 200.332. The following certifications and assurances are required to be imposed upon subrecipients and contractors. They are:

- Non-discrimination

- Political Activity (Hatch Act)

- Certification Regarding Federal Lobbying

- Restriction on State Lobbying

- Certification Regarding Debarment and Suspension

- Buy America Act

- Prohibition on Using Grant Funds to Check for Helmet Usage

- For FY 2024, Certification of Conflict of Interest.

The HSO may at their option require additional subrecipient State certifications and assurances, such as, seat belt use or training requirements for law enforcement officers.

The HSO shall have a written procedure to ensure subrecipients are not suspended or debarred and that there is written documentation that the SHSO is complying with the procedure. The HSO shall ensure annually that each subrecipient is checked on the website: https://www.sam.gov/SAM/ to ensure they are not suspended or debarred.

Subrecipients are required to become familiar with the contents of the final grant agreement form and be on notice that failure to do so will not excuse nonperformance or noncompliance.

If a non-Federal entity fails to comply with Federal statutes, regulations or the terms and conditions of a Federal award, the Federal awarding agency or pass-through entity may impose additional conditions, as described in 2 CFR Part 200.208 Specific conditions, or terminate the award in whole or part as provided in 2 CFR Part 200.340.

Each fiscal year the HSO signs Certifications and Assurances with the submission of Appendix A of the AGA that the State complies with all applicable Federal statutes, regulations, and directives in effect with respect to the period for which it is receiving grant funding.

See Chapter II. Planning – Section N. Certifications and Assurances for additional information.

### E. NHTSA Equipment Purchase and Disposition Approval of $5,000 or More

This section establishes the process for grant agreements which include the purchase of equipment which has a useful life of more than one year and a cost of $5,000 or more.

For all major equipment purchases and replacement purchases with a useful life of more than one year and an acquisition cost of $5,000 or more in value including software/information technology systems, the HSO shall receive prior written approval from the NHTSA Regional Administrator. This procedure is required by 23 CFR Part 1300.31. Acquisition cost is defined at 2 CFR Part 200.1. Ancillary charges, such as taxes, duty, freight and installation, may need to be included dependent on the State’s (non-federal entity) regular accounting practices. The costs included or excluded must be consistent with the State’s accounting practice. If a relevant State accounting practice does not exist, then the default is to include the taxes and fees as typical components of net invoice cost.

The regulations look to the cost of the equipment regardless of the portion of funding supported by Federal or other funds if the total cost was $5,000 or more. See also 2 CFR Part 200.439 on capital equipment.

The HSO shall include a subrecipient procedure in the Project Director’s Manual for purchases of major equipment of $5,000 or more in value in accordance with the applicable State and NHTSA regulations and describe allowable and unallowable equipment purchases as specified by the Federal regulations. The unit cost for equipment is the unit’s purchase price plus any accessories necessary to make the equipment operational for its intended purpose.

During the review of proposed grant applications, the [insert position title] shall identify all equipment purchase requests by subrecipients which meet the above criteria. The [insert position title] shall ensure that the equipment has been identified within the project listed in the HSO AGA (inclusion of the equipment request within the HSP is not mandatory but is preferred and that written approval from NHTSA has been obtained by preparing a letter to be signed by the HSO Administrator and then submitted to the NHTSA Regional Administrator for specific approval.) The letter request shall describe the type of and a complete description of the equipment, subrecipient’s organization name, total cost, useful life and how the equipment would support the State’s THSP.

If approved, the HSO shall inform the subrecipient to proceed with the equipment purchase by sending a written communication and providing specific instructions for the purchase of the equipment.

Before initiating the purchase of new and replacement equipment with a useful life of more than one year and an acquisition cost of $5,000 or more, a subrecipient must obtain written notice from the HSO Administrator stating that both HSO and the NHTSA Regional Administrator have formally approved the equipment purchase. When making the equipment purchase, the purchaser should also obtain the expected service life and warranty of the equipment from the vendor or the manufacturer.

[NOTE: The HSO typically provides grant funds for traffic-related law enforcement equipment. Specific requirements pertaining to the purchase of law enforcement equipment may be identified here.]

The NHTSA guidance has stated that costs for construction, rehabilitation or remodeling of any buildings or structures or for the purchase of office furnishings and fixtures are unallowable. The following are some examples:

| chair table shelving coat rack | bookcase filing cabinet floor covering office planter | portable partition pictures or wall clock draperies and hardware fixed lighting/ lamp. |
| --- | --- | --- |

See also unallowable items listed in the NHTSA Management Review Elements for FY23 Only, Section II. Program Management (F)(5)(g).

The HSO, as part of its oversight responsibility, shall systematically monitor all subrecipients with grant-funded equipment in accordance with State laws and procedures to ensure that subrecipients are in compliance with all Federal and any State requirements for property management, inventory and disposition.

Equipment shall be used by the subrecipient for the purpose for which it was acquired as long as needed, regardless of whether the program continues to be supported by HSO funds. When no longer needed for the original program, the equipment may be used in other traffic safety activities. If it is determined that the equipment is no longer needed for the purpose acquired or any other traffic safety purpose, the equipment shall be handled in accordance with HSO policy and Federal requirements.

Prior written approval must be received from the NHTSA Regional Office by the HSO for the disposition of equipment with a value of $5,000 or more unless the equipment has exceeded its useful life as determined under State law and procedures.

See Chapter V. Grant Administration and Management, Section G. Property Management

### F. Reporting Requirements

This section describes the HSO reporting requirements for subrecipients.

[NOTE: The HSO requirements regarding frequency of reporting and deadlines as described in the following policy may vary in your State.]

The HSO requires three types of progress reports in conjunction with traffic safety grant projects: periodic progress reports during the life of a grant, a final report at the conclusion of a grant (this is to include training and consultant reports, if applicable), and special reports as required, see 2 CFR Part 200.332(d)(1).

Progress reports provide the HSO with information that can be used to strengthen the State’s overall traffic safety program. These reports should keep the HSO informed of a grant’s progress, explain any difficulties encountered, provide background information that can be shared with others, and suggest ways in which the HSO can assist and aid in the distribution of funds.

i. Quarterly Progress Reports

The reports are to be submitted quarterly and are due in the HSO within not less than thirty (30) calendar days after the end of the reporting month. A report must be filed every quarter regardless of whether no activity has taken place, or no grant related expenditures have occurred. The HSO [insert position title] shall provide a calendar of report due dates to each subrecipient.

The report should indicate if no progress has been made on the project. Any original or innovative ideas or methods employed in the project should be incorporated into the reports.

A progress report is required with each submission of an invoice to the HSO for cost reimbursement.

ii. Final Progress Report

Final reports are due from subrecipients to the HSO no later than November 15 for activities funded in the previous fiscal year. The reports are to be detailed and must describe whether the grant objectives were accomplished, if technical and fiscal problems were encountered, and what improvements in traffic safety have resulted or probably will result. Included in final reports will be copies of publications, training reports and any statistical data generated in grant execution. Final reports should discuss the following:

- Accomplishments compared to the original grant objectives.

- Were all activities of the grant completed as scheduled?  Dates and milestones when studies were completed should be included.

- Equipment purchased should be identified.

- Any unanticipated issues that affected the grant.

- Funding and costs for completion of the grant in relationship to the original estimates.

- Third party performance if applicable. A copy of any consultant reports should be included with the final report.

- A budget clearly identifying remaining budgetary balances.

iii. Special Progress Reporting

Special reporting may be required. If so, reporting frequency and requirements will be detailed by the HSO in the grant agreement. However, performance reports should not be required more frequently than quarterly except for unusual circumstances or special request.

### G. Grant and THSP Revisions

This section identifies the process which must be completed when a subrecipient requests a revision to a proposed grant application or a final grant agreement.

[NOTE: The HSO policy regarding revisions as described below may vary in the State.]

Proposed grant applications and final grant agreements may be altered or amended prior to or after signing by mutual agreement of the parties. The alterations or amendments are not binding unless they are in writing and signed by persons authorized to bind each of the parties. The signature of the [insert position title] is necessary to bind the HSO.

Proposal alterations or amendments that extend the period of performance without the expenditure of funds in the new fiscal year (a no-cost time extension) are permitted with the prior approval of the HSO. If additional tasks or costs are authorized in the amendment, the subrecipient must not begin work on the additional tasks or incur the additional costs until the amendment is fully executed. An amendment cannot be used to authorize new or different work not related to the scope of the grant being amended.

Subrecipients must have any amendments to a grant executed not less than 60 days prior to the end of the applicable grant year.

[NOTE: This policy may vary by State.]

The following deviations from the approved grant budget require PRIOR approval from the HSO:

- A specific item of cost not included in the approved budget.

- An increase in the number of a specific item over and above the total authorized

- A transfer between major budget categories in excess of a total of 10 percent of the category being increased. (For transfers of less than a total of 10 percent of the category being increased, an email notification describing the action being taken shall be sent to the HSO by the subrecipient.)

The HSO procedure for review and approval of grant agreement revisions is:

- Subrecipient submits email or phone request for a grant agreement revision.

- [insert position title] provides subrecipient with a Grant Revision Form [NOTE: Insert form number and link if available]

- Subrecipient completes and submits the Grant Revision Form to the HSO

- [insert position title] reviews the Grant Revision Form and makes a recommendation for approval or denial.

- If recommended for approval, an AGA amendment is submitted to the NHTSA Regional Administrator for approval, see below REVISIONS.

- If the approval is received from NHTSA, the [insert position title] forwards the Grant Revision Form to the HSO Administrator for approval and notifies the subrecipient in writing. The [insert position title] then issues a Notice to Proceed to the subrecipient. All related paperwork is retained in the grant file. If the grant revision results in an addition of funds to the original grant agreement, the [insert position title] will revise the Grant Tracking Spreadsheet (See Chapter VI. Fiscal Procedures, Section D. Grant Tracking Spreadsheet). If the subrecipient is a State agency, an amended [insert form name] form shall also be prepared by the [insert position title].

- If recommended for denial, the [insert position title] prepares an explanation for the denial and notifies the subrecipient. All related paperwork is retained in the grant file.

REVISIONS: In some circumstances, the HSO decides to make a revision to the approved THSP within the AGA. During the fiscal year of the grant, except performance targets, after approval of the annual THSP under 23 CFR Part 1300.12, the HSO shall document “changes” to the HSP electronically.

Following the approval of the THSP by NHTSA, the HSO shall submit the AGA to NHTSA for approval prior to beginning project performance and provide the information about each signed project agreement in which it plans to enter, see Chapter II. Planning, Section B(ii) AGA Contents:

Amendments to the AGA are subject to the approval of the NHTSA Regional Administrator (RA). The RA must approve any changes to the AGA before approval of vouchers for payment. The RA will disapprove changes and projects that are inconsistent with the HSP or that do not constitute an appropriate use of Federal funds. See 23 CFR Part 1300.12(d) .

### H. Development of Highway Safety Office Internal Grants

This section establishes the requirement for development of the internal HSO grant agreements to fund all related costs of the highway safety program operation.

In anticipation of the beginning of each new fiscal year, the HSO Administrator and [insert position title] will estimate how much funding is needed for Planning and Administration (P&A) and Program Management costs to support the operation of the HSO highway safety program. Estimates will take into consideration any anticipated increases in costs as well as in recurring costs. A proposed grant application form will be completed and approved for each program operated by the HSO and will describe the problem identification, targets, objectives, activities, performance measures and a budget narrative for the upcoming year. Both HSO internal grant agreements will be approved by [insert position title] who will also be designated as the Project Director for the HSO P&A grant. The HSO Administrator will be designated as the Project Director for the HSO Program Management grant. The HSO shall ensure that the internal grants are developed and approved by the Department by September 30 of each fiscal year.

Definition of P&A Costs: P&A costs are those direct and indirect expenses that are attributable to the overall management of the State's Highway Safety Agency. Costs include salaries and related personnel benefits for the Governor’s Representative for Highway Safety and for other technical, administrative, and clerical staff, for the HSO. P&A costs also include other costs, such as travel, equipment, supplies, rent and utility expenses necessary to carry out the functions of the HSO. Centralized support services such as personnel, procurement and budgeting would be indirect costs. See 23 CFR Part 1300(a) Planning and Administration (P&A) costs.

Definition of Program Management Costs: Program management costs are those direct and indirect expenses that are attributable to the highway safety program area. Costs include salaries and related personnel benefits and other related costs such as travel, equipment, materials and supplies. See 23 CFR Part 1300(a) Planning and Administration (P&A) costs.

All costs related to internal operation of the HSO program will be charged only to the HSO internal grants.

i. P&A Match Requirement

The [insert position title] and HSO Administrator shall ensure that the internal P&A grant complies with applicable Federal regulations including the provision of a match of State or local funds in the amount of 50 percent (or the applicable sliding scale rate) of the costs claimed for eligible P&A functions. These requirements are explained in the NHTSA August 2019 Memo Guidance on Match. See Chapter VI. Fiscal Procedures, Section C. Matching Funds

Match is defined as the direct expenditure of actual State funds or State or local funds that are expended in support of other qualifying traffic safety programs. The required P&A match expenses can be a cash match (hard) and/or in-kind contributions (soft) (see footnote 3 of the NHTSA Memo).  P&A soft match expenditures are required to be an SHSO-related P&A expense unlike other Section 402 and Section 405 program matches which can be any eligible State or local expenditures under those programs.  P&A soft match cannot be included in the State’s indirect cost rate charged to its federal grant.  P&A costs are those direct and indirect costs that are attributable to management of the SHSO program. Like other match, the match expenses cannot be used to match any other federal program and documentation must be maintained to support an audit.

Unexpended balances of funds obligated to planning and administration may be carried forward into the succeeding FY as planning and administration if they were programmed in GTS by September 30.

The Federal P&A share shall not exceed 50 percent of total P&A costs, except for select States using the sliding scale for match (See NHTSA Order 462-6C Matching Rates for State and Community Highway Safety Program at NHTSA Highway Safety Grant Program Resources). No match is required for Section 163, Section 406, Sections 154 or 164 funds transferred to Section 402 purposes, for U.S. Territories (23 U.S.C. 120(i)), or for Federally recognized Indian Tribal governments (as defined by 23 CFR 402 (h)) under the Indian highway safety program. From its annual State appropriations, the Department shall ensure the availability of the funds needed by the HSO to support the program match for the State’s P&A share. If the State is using any HSO indirect costs as a P&A match, the costs shall only be applied to P&A expenditures.

The HSO shall limit Federal participation in P&A funding to not exceed 50 percent (or the applicable sliding scale rate) of the total cost of such activities. The HSO shall ensure that the Federal contribution does not exceed 18 percent beginning FY 2024) of the total new funds the State receives annually under Section 402, and, for Section 154 and 164 transfer funds. The amount a State allocates for Section 154 and/or Section 164 P&A must be related to the costs for planning and administration of the impaired-driving programs supported with the specific transfer funds used.

If a HSO is found by NHTSA to have miscalculated or not provided sufficient P&A match, the correct amount will be determined by NHTSA and the HSO will be required to take the appropriate corrective action.

ii. HSO Employee Time Allocation and Certification Requirements

As provided by 2 CFR Part 200.430, charges to Federal awards for salaries and wages, whether treated as direct or indirect costs, will be based on payrolls documented in accordance with the generally accepted practice of the governmental unit and approved by a responsible official(s) of the governmental unit.

2 CFR Part 200.430 requires the HSO to rely on strong internal control standards for both employee and subrecipient time and attendance records although flexibility is allowed on how to meet those standards. A sample of timesheets may be examined during a NHTSA Management Review.

Biannual certifications and personnel activity reports (PAR) are no longer required although the HSO is encouraged to choose to use them. Charges to Federal awards for salaries and wages must be based on records that accurately reflect work performed. 2 CFR Part 200.430(1) (i) establishes, Standards for Documentation of Personnel Expenses and subsection (8) states that where the records of the subrecipient does not meet these standards, the Federal agency may require PARs including certifications that support the records as required by this section.

For HSO employees working on P&A functions, the HSO shall ensure that only direct and indirect expenses for salaries and other costs that are attributable to the overall management of the State's HSP and necessary to carry out its functions are charged to P&A. The HSO shall ensure that employees who process grant claims or perform other P&A type duties are working on P&A for only the applicable fund program type e.g., an employee charging 100% to 410 or 154 P&A must work on P&A only for applicable programs.  23 CFR Part 1300(13(a)(4) states that if the HSO elects to allocate costs based on actual time spent on an activity, the recordkeeping system must keep accurate time records and show the work activities for each employee.

The HSO shall periodically examine the process and the cost data used to determine employee time allocation and certification methods to ensure continued accuracy and amend the data when significant changes occur. The HSO shall ensure that documentation for costs vouchered to P&A and program management are charged as described in the THSP.

The HSO shall periodically determine compliance through review of the HSO employee timesheets to verify the time distribution and costs by employee position and specific program to ensure that P&A and program funds are being appropriately charged.

iii. Time and Attendance Records

All employee time and attendance records shall be signed by the appropriate supervisor or timekeeper as required by State law, regulation, rule, policy or guideline. The attendance record of salaried employees should also be accurately documented whether federally funded or funded by State match. There are sample time certification and timekeeping forms provided on the GHSA web site in the Members Only section under Planning and Management Tools, Sample SHSO Personnel Activity Reports.

LEAVE TIME: When an employee is charging time to more than one award (e.g., 402 and 405) the allocation of leave time must be equitably and reasonably charged to the funds. The HSO may choose at the beginning of the year to cost allocate leave time throughout the year based on proportional work, number of projects and/or funds managed. The cost of fringe benefits in the form of regular compensation paid to employees during periods of authorized absences, such as annual leave, sick leave, holidays, etc., are allowable if: they are provided under established written leave policies, the costs are equitably allocated to all related activities including Federal awards, and, the accounting basis (cash or accrual) selected for costing each type of leave is consistently followed by the governmental unit, see 2 CFR Part 200.431.

iv. Subrecipient Timekeeping Requirements

Subrecipients of Federal awards are subject to the same requirements for time allocation and certification as the primary award recipients. The HSO shall ensure that subrecipients are informed of the applicable Federal time allocation and certification requirements and are operating in compliance by periodically examining their records to verify full compliance with these provisions. A sample of subrecipient timesheets may be examined during a NHTSA Management Review.

v. HSO Invoicing and Reporting

The HSO shall complete and submit at least quarterly invoices to NHTSA to request Federal reimbursement for allowable costs and prepare periodic progress reports for documenting the activities completed for the two internal grants. Regardless, if the HSO receives or expends more that $1 million annually, then a voucher shall be submitted monthly and within 15 working days of the end of each month.

See Section F. Reporting Requirements, for additional information regarding subrecipient progress reports.